## ADMINISTRATIVE TASK LIST
ECE - 4981 SENIOR DESIGN ADMINISTRATIVE TASK LIST FALL 2020 - WINTER 2021 | [6 empty] | Members: Abdullah - Matt - HD |  |  | STATUS MENU | Ongoing | PRIORITY MENU | High
[7 empty] | Advisor: Paul Watta |  |  |  | Not Started |  | Low
[7 empty] | Project: Project's Name |  |  |  | Done |  | Medium
TASK NO. | TASK DESCRIPTIONS | PRIORITY | ASSIGNEE | START DATE | DUE DATE | DAYS LEFT | STATUS | DOCUMENTS | COMMENTS |  | Late
1 | Create a task list using excel spreadsheet |  | HD | 2020-09-05 | 2020-09-08 | 0 | Done |  | The task list used to keep track of the main tasks and sub-tasks that need to be done in order to complete the senior design project. The task list also includes dates, priorities, assignees' initials, status, and comments. 09/05/20 Created the template for the task list. Will add more tasks, sub-tasks and deadline later.
2 | Team formation |  | HD/MF/AA | 2020-09-08 | 2020-09-11 | 0 | Done |  | Will work on this when the team meet on Sep 8
| Finalize team members | [5 empty] | Done |  | 3 team members
| Determine team name | [5 empty] | Done |  | Sound Logic
| Determine project name | Low | HD/MF/AA | [5 empty] | Will need to discuss and have concept description before working on this task
| Discuss project concepts (Resonator part) |  | HD/MF/AA |  |  |  | Ongoing | If you have the ppt you can make a link to the document here | 09/08/20 Matt to make a ppt slides on principle of a resonator
| Contact faculty advisor |  | MF |  |  |  | Done |  | 09/10/2020 Professor Paul Watta has accepted our invitation to be our faculty advisor. Matt Falconer will set up a vrtual meeting with him for next week in which we can discuss our project concepts and receive written advisor comments.
3 | Draft Concept Description with advisor comments | High | HD/MF/AA |  | 2020-09-18 | 5 | Ongoing |  | When meeting on Sep 8, we should discuss and determine the sub-tasks for this task. Wait until receiving template from prof
| What is required to have in a concept description |  | HD | 2020-09-11 | 2020-09-15 | 2 | Ongoing |  | 09/11/20 HD to make a ppt slides to present what should be included in a concept description before next group meeting. 09/12/20 Have gathered info from all posible good sources for the documentation. Sources: Prof Paul Richarson, ECE4951, and Embedded Systems - Shape the World Micocontroller I/O by Valvano.
| Team meeting to assign tasks on draft concept description |  | HD/MF/AA |  | 2020-09-17 | 4 | Not Started
| Send a draft concept description to Prof Watta and set up a meeting with Prof |  | MF |  | 2020-09-16 | 3 | Not Started
| Meet with Prof Watta to have inputs, thoughts, comments |  | HD/MF/AA |  | 2020-09-17 | 4 | Not Started
4 | Present Concept Description | Medium | HD/MF/AA |  | 2020-09-21 | 6 | Not Started
5 | Final concept description report | Medium | HD/MF/AA |  | 2020-09-25 | 10 | Not Started
6 | First definition of planned excursions with advisor comments | Low | HD/MF/AA |  | 2020-10-02 | 15 | Not Started
7 | ROM budget | Low | HD/MF/AA |  | 2020-10-09 | 20
8 | Draft SRR with advisor comment | Low | HD/MF/AA |  | 2020-10-16 | 25 | Not Started
9 | SRR: system requirements review | Low | HD/MF/AA |  | 2020-10-19 | 26 | Not Started
10 | Final requirements, specifications, and draft test plan | Low | HD/MF/AA |  | 2020-10-23 | 30 | Not Started
11 | Demonstrate excursion 1 results | Low | HD/MF/AA |  | 2020-10-26 | 31 | Not Started
12 | Second definition of planned excursions with advisor comments | Low | HD/MF/AA |  | 2020-11-06 | 40 | Not Started
13 | Demonstrate excursion 2 results | Low | HD/MF/AA |  | 2020-11-16 | 46
14 | Draft High Level Design Spec with advisor comments | Low | HD/MF/AA |  | 2020-11-20 | 50
15 | Peer review High Level Design | Low | HD/MF/AA |  | 2020-11-30 | 56
16 | Draft High Level Design Specification with advisor comments | Low | HD/MF/AA
17 | PDR High Level Design review | Low | HD/MF/AA |  | 2020-12-07 | 61
18 | Final High Level Design Specification | Low | HD/MF/AA |  | 2020-12-11 | 65
Formulas:
DAYS LEFT = IF([Members: Abdullah - Matt - HD]="Done",0,(NETWORKDAYS.INTL(TODAY(),[DUE DATE])))
DAYS LEFT = (NETWORKDAYS.INTL(TODAY(),[DUE DATE]))

## ENGINEERING TASK LIST
ECE - 4981 SENIOR DESIGN ENGINEERING TASK LIST FALL 2020 - WINTER 2021 | [6 empty] | Members: Abdullah - Matt - HD |  |  | STATUS MENU | Ongoing | PRIORITY MENU | High
[7 empty] | Advisor: Paul Watta |  |  |  | Not Started |  | Low
[7 empty] | Project: Project's Name |  |  |  | Done |  | Medium
TASK NO. | TASK DESCRIPTIONS | PRIORITY | ASSIGNEE | START DATE | DUE DATE | DAYS LEFT | STATUS | DOCUMENTS | COMMENTS |  | Late
1 | Sound Production Module Development |  | MF | 2020-09-14 | 2020-12-11 | 65
| Define system sound power output requirements |  | MF | 2020-09-14 | 2020-10-16 | 25
| Define system frequency output requirements |  | MF | 2020-09-14 | 2020-10-16 | 25
| Define system amplitude output requirements |  | MF | 2020-09-14 | 2020-10-16 | 25
| Select a loudspeaker device based on defined sound output requirements |  | MF | 2020-09-14 | 2020-11-20 | 50
| Design loudspeaker mounting hardware for selected loudspeaker device |  | MF
| Select an audio signal amplifier device based on the selected loudspeaker device, sound power output requirements, and the selected Control CPU device. |  | MF and HD | 2020-09-14 | 2020-11-20 | 50
| Select audio signal wiring hardware based on expected audio signal power levels |  | MF and HD | 2020-09-14 | 2020-11-20 | 50
2 | Control CPU Module Development |  | HD | 2020-09-14 | 2020-12-11 | 65
| Define system Control CPU analog and digital signal output capability requirements |  | HD and MF | 2020-09-14 | 2020-10-16 | 25
| Define system Control CPU user interface requirements |  | HD and MF | 2020-09-14 | 2020-10-16 | 25
| Select Control CPU device(s) based on signal output and user interface requirements |  | HD | 2020-09-14 | 2020-11-20 | 50
| Select and install a programming interface for the selected Control CPU devices (C/C++ compiler, MATLAB installation, etc) |  | HD
| Use Fourier Synthesis and/or Subtractive Synthesis techniques to create a simple digital frequency generator program within the Control CPU |  | HD
| Expand the digital frequency generator program to include digital control outputs for the electronic valve actuators |  | HD
3 | Valve Actuation Module Development |  | AA | 2020-09-14 | 2020-12-11 | 65
| Define valve actuator mechanical requirements based on provided brass instrument valve design specifications |  | AA and MF | 2020-09-14 | 2020-10-16 | 25
| Select an electronic valve actuator device based on the valve actuator mechanical requirements |  | AA | 2020-09-14 | 2020-11-20 | 50
| Select a power transistor device based on valve actuator electric input specifications, and Control CPU electric output specifications |  | AA and HD | 2020-09-14 | 2020-11-20 | 50
| Select a DC voltage source device based on electric specifications of the selected valve actuator and power transistor |  | AA | 2020-09-14 | 2020-11-20 | 50
| Select actuator signal wiring hardware based on expected signal power levels |  | AA | 2020-09-14 | 2020-11-20 | 50
| Design a mounting solution for the electronic valve actuators |  | AA
Formulas:
DAYS LEFT = (NETWORKDAYS.INTL(TODAY(),[DUE DATE]))
DAYS LEFT = IF([Members: Abdullah - Matt - HD]="Done",0,(NETWORKDAYS.INTL(TODAY(),[DUE DATE])))