## TASK LIST
ECE - 4981 SENIOR DESIGN TASK LIST FALL 2020 - WINTER 2021 | [6 empty] | Members: Abdullah - Matt - Hung |  | STATUS MENU | Ongoing | PRIORITY MENU | High
[7 empty] | Advisor: Advisor's Name |  |  | Not Started |  | Low
[7 empty] | Project: Project's Name |  |  | Done |  | Medium
TASK NO. | TASK DESCRIPTIONS | PRIORITY | ASSIGNEE | START DATE | DUE DATE | DAYS LEFT | STATUS | COMMENTS |  | Late
1 | Create a task list using excel spreadsheet | Medium | HD | 2020-09-05 | 2020-09-08 | 1 | Done | The task list used to keep track of the main tasks and sub-tasks that need to be done in order to complete the senior design project. The task list also includes dates, priorities, assignees' initials, status, and comments. 09/05/20 Created the template for the task list. Will add more tasks, sub-tasks and deadline later.
2 | Team formation | High | HD/MF/AA | 2020-09-08 | 2020-09-11 | 4 | Ongoing | Will work on this when the team meet on Sep 8
| Finalize team members | [5 empty] | Done | 3 team members
| Determine team name | [5 empty] | Done | Sound Logic
Determine project name
| Discuss project concepts | [5 empty] | Ongoing | 09/08/20 Matt to document the problems
| Contact faculty advisor | High | MF |  |  |  | Ongoing | 09/08/20 How many advisors can we have? Prof Putty (backup Prof: John Miller, Larry Sieh, Azeem H.) Contact and Set up a meeting with the advisor
3 | Draft Concept Description with advisor comments | Medium | HD/MF/AA |  | 2020-09-18 | 9 | Not Started | When meeting on Sep 8, we should discuss and determine the sub-tasks for this task. Wait until receiving template from prof
4 | Present Concept Description | Medium | HD/MF/AA |  | 2020-09-21 | 10 | Not Started
5 | Final concept description report | Low | HD/MF/AA |  | 2020-09-25 | 14 | Not Started
6 | First definition of planned excursions with advisor comments | Low | HD/MF/AA |  | 2020-10-02 | 19 | Not Started
7 | ROM budget | Low | HD/MF/AA |  | 2020-10-09 | 24
8 | Draft SRR with advisor comment | Low | HD/MF/AA |  | 2020-10-16 | 29 | Not Started
9 | SRR: system requirements review | Low | HD/MF/AA |  | 2020-10-19 | 30 | Not Started
10 | Final requirements, specifications, and draft test plan | Low | HD/MF/AA |  | 2020-10-23 | 34 | Not Started
11 | Demonstrate excursion 1 results | Low | HD/MF/AA |  | 2020-10-26 | 35 | Not Started
12 | Second definition of planned excursions with advisor comments | Low | HD/MF/AA |  | 2020-11-06 | 44 | Not Started
13 | Demonstrate excursion 2 results | Low | HD/MF/AA |  | 2020-11-16 | 50
14 | Draft High Level Design Spec with advisor comments | Low | HD/MF/AA
15 | Peer review High Level Design | Low | HD/MF/AA |  | 2020-11-30 | 60
16 | Draft High Level Design Specification with advisor comments | Low | HD/MF/AA
17 | PDR High Level Design review | Low | HD/MF/AA |  | 2020-12-07 | 65
18 | Final High Level Design Specification | Low | HD/MF/AA
Formulas:
DAYS LEFT = (NETWORKDAYS.INTL(TODAY(),[DUE DATE]))