## TASK LIST
ECE - 4981 SENIOR DESIGN TASK LIST FALL 2020 - WINTER 2021 | [6 empty] | Members: Abdullah - Matt - HD |  | STATUS MENU | Ongoing | PRIORITY MENU | High
[7 empty] | Advisor: Paul Watta |  |  | Not Started |  | Low
[7 empty] | Project: Project's Name |  |  | Done |  | Medium
TASK NO. | TASK DESCRIPTIONS | PRIORITY | ASSIGNEE | START DATE | DUE DATE | DAYS LEFT | STATUS | COMMENTS |  | Late
1 | Create a task list using excel spreadsheet | Medium | HD | 2020-09-05 | 2020-09-08 | 0 | Done | The task list used to keep track of the main tasks and sub-tasks that need to be done in order to complete the senior design project. The task list also includes dates, priorities, assignees' initials, status, and comments. 09/05/20 Created the template for the task list. Will add more tasks, sub-tasks and deadline later.
2 | Team formation | Low | HD/MF/AA | 2020-09-08 | 2020-09-11 | 1 | Ongoing | Will work on this when the team meet on Sep 8
| Finalize team members | [5 empty] | Done | 3 team members
| Determine team name | [5 empty] | Done | Sound Logic
Determine project name
| Discuss project concepts | Medium | HD/MF/AA |  |  |  | Ongoing | 09/08/20 Matt to the working principle of a resonator
| Contact faculty advisor | High | MF |  |  |  | Done | 09/10/2020 Professor Paul Watta has accepted our invitation to be our faculty advisor. Matt Falconer will set up a vrtual meeting with him for next week in which we can discuss our project concepts and receive written advisor comments.
3 | Draft Concept Description with advisor comments | High | HD/MF/AA |  | 2020-09-18 | 6 | Ongoing | When meeting on Sep 8, we should discuss and determine the sub-tasks for this task. Wait until receiving template from prof
| What is required to have in a concept description |  | HD | 2020-09-11 | 2020-09-13 | 1 | Ongoing | 09/11/20 HD to make a ppt slides to present what should be included in a concept description before next group meeting.
| Team meeting to assign tasks on draft concept description |  | HD/MF/AA
Send a draft concept description to Prof Watta and set up a meeting with Prof
Meet with Prof Watta to have inputs, thoughts, comments
4 | Present Concept Description | Medium | HD/MF/AA |  | 2020-09-21 | 7 | Not Started
5 | Final concept description report | Low | HD/MF/AA |  | 2020-09-25 | 11 | Not Started
6 | First definition of planned excursions with advisor comments | Low | HD/MF/AA |  | 2020-10-02 | 16 | Not Started
7 | ROM budget | Low | HD/MF/AA |  | 2020-10-09 | 21
8 | Draft SRR with advisor comment | Low | HD/MF/AA |  | 2020-10-16 | 26 | Not Started
9 | SRR: system requirements review | Low | HD/MF/AA |  | 2020-10-19 | 27 | Not Started
10 | Final requirements, specifications, and draft test plan | Low | HD/MF/AA |  | 2020-10-23 | 31 | Not Started
11 | Demonstrate excursion 1 results | Low | HD/MF/AA |  | 2020-10-26 | 32 | Not Started
12 | Second definition of planned excursions with advisor comments | Low | HD/MF/AA |  | 2020-11-06 | 41 | Not Started
13 | Demonstrate excursion 2 results | Low | HD/MF/AA |  | 2020-11-16 | 47
14 | Draft High Level Design Spec with advisor comments | Low | HD/MF/AA
15 | Peer review High Level Design | Low | HD/MF/AA |  | 2020-11-30 | 57
16 | Draft High Level Design Specification with advisor comments | Low | HD/MF/AA
17 | PDR High Level Design review | Low | HD/MF/AA |  | 2020-12-07 | 62
18 | Final High Level Design Specification | Low | HD/MF/AA
Formulas:
DAYS LEFT = IF([Members: Abdullah - Matt - HD]="Done",0,(NETWORKDAYS.INTL(TODAY(),[DUE DATE])))
DAYS LEFT = (NETWORKDAYS.INTL(TODAY(),[DUE DATE]))